## Risk Analysis
RISK ID | RISK TITLE | SEVERITY | LIKELIHOOD OF A RISK | RISK OF DETAIL | SYSTEMS IMPACTED | RISK OWNER | WORKAROUND | MITIGATION PLAN | IMPACT ID
R001 | Website Downtime | H | L | Server crashes or technical issues causing the website to go offline. | IT/Development, Sales | IT/Development | Redirect traffic to backup servers, display a maintenance page or restore system to last known stable restore point | Invest in scalable infrastructure, load balancing, regular system maintenance and running periodic regression to ensure stability | I001
I002
I003
R002 | Payment Gateway Failure | H | L | Payment processing system fails, leading to abandoned carts and lost sales. | Finance, IT/Development, Sales | IT/Development | Offer alternative payment methods | Regularly test payment gateways, and maintain backup payment options | I004
I005
I006
R003 | Poor User Experience (UX) | L | M | Slow website performance, confusing navigation, broken links, and inaccessibility | UI/UX, IT/Development | UI/UX | Provide a simplified version of the website, improve caching mechanisms, reponsive UI, accessibility considerations and customer oriented approach | Conduct regular UI/UX testing, optimize website speed, fix broken links, implementing web caching mechanism, improving navigation flows. | I007
I008
I009
R004 | Cybersecurity Breach | H | L | Unauthorized access and loss of customer data, payment information, internal systems and potential risk of website downtime | Cybersecurity | Cybersecurity | Temporary shutdown of affected systems, enhanced monitoring, notify customers and cross-teams of the breach | Implement advanced firewalls and security measures, MFA (multi-factor authentication), regular penetration testing, and employee training. | I010
I011
I012
R005 | Slow Page Load Times | L | L | High page load times can lead to decreased user satisfaction and reduced conversion rates. | IT, Sales | IT/Development | Optimize images, browser caching mechanisms, and minimize server response times to improve load speeds. | Regularly monitor site performance and conduct performance tests to identify and address bottlenecks promptly. | I013
I014
I015

## Impact Analysis
IMPACT ID | IMPACT TITLE | IMPACT DESCRIPTION | IMPACT ON DIFFERENT SYSTEMS | ITEM OWNER | PRIORITY
I001 | Loss of revenue | Extended downtime can lead to significant loss in sales, especially during peak shopping seasons like Black Friday or holidays. | Finance, IT, Sales | Finance | H
I002 | Damaged brand reputation | Frequent downtime can reduce customer confidence, leading to lower retention rates and damage to brand reputation. | Sales, UI/UX, IT | Marketing | H
I003 | Lower customer retention | Customers may switch to competitors if they experience frequent downtime on the website | Sales, IT, UI/UX | Customer Support & Experience | H
I004 | Abandoned Carts | Customers may abandon their carts if they cannot complete purchases, leading to loss of sales and revenue. | IT, Sales | Sales | H
I005 | Negative Customer Experience | Frustrated customers may leave negative reviews or share their poor experience on social media, denting the brand's reputation | UI/UX, IT, Sales | UI/UX | M
I006 | Operational Disruptions | Internal teams may face delays in processing orders, refunds, and reconciliations, leading to inefficiencies. | IT, Security, Finance | Website Admins | H
I007 | Increased Bounce Rate | Users may leave the site quickly if they find the navigation difficult or the performance slow, reducing engagement. | UI/UX, IT | UI/UX | M
I008 | Negative Brand Perception | Poor UX can lead to complaints on social media, review platforms, word of mouth and customer support channels | UI/UX, Sales, Marketing | Marketing | M
I009 | Lower Sales & Conversion Rates | A cluttered or slow interface may prevent users from easily finding and purchasing products, leading to revenue loss. | UI/UX, Sales, IT | Sales | H
I010 | Legal and Regulatory Penalties | The organization may face fines, lawsuits, or compliance issues if customer data is compromised, especially under strict digital privacy regulations | Security, Regulatory bodies, IT | Regulatory Bodies | H
I011 | Financial Losses | Costs associated with breach remediation, customer compensation, and potential ransomware payments can significantly impact the organization's finances. | Security, Finance | Finance | H
I012 | Operational Disruptions | The organization may temporarily shut down parts of its online system to contain the breach, affecting order processing and fulfillment. | Operations, Security, IT, Sales | Security | H
I013 | Decreased User Engagement | Slow-loading pages can frustrate users, leading to reduced time spent on the site and fewer interactions with products. | IT, UI/UX | UI/UX | M
I014 | Lower Search Engine Rankings | Search engines like Google may downgrade the visibility in search results. | IT, UI/UX | IT (SEO) | M
I015 | Missed Sales Opportunities | Slow page loads can cause customers to abandon the site before completing purchases, especially during high-traffic events like sales or promotions. | IT, Sales, UI/UX | Sales | H