## RACI Matrix
|  | Executive Leadership | Requirement Gathering | UI/UX |  | IT/Development |  |  |  |  | Deployment
|  | Directors/ CEO | Business Analyst | UX Head | UI/UX Designer Team | Project Manager | Subject Matter Expert (SME) | Technical Lead | Developers | QA/ Lead | DevOps
Planning | Deliverable Document Names
– Define project scope and objectives | Project Charter | C | R | C |  | R/A | C | I |  | I
– Identify key stakeholders | Stakeholder Analysis | I | R | C |  | A | C
– Develop a project timeline & milestones | Project Plan | I | R | C |  | R/A | C | C |  | C | C
– Perform risk & impact assessment | Risk & Impact Analysis | I | R | C |  | A | C |  |  | C | C
– Define roles & responsibilities | RACI Matrix | I | R |  |  | A
– Approval process | Approval Sign-Off Document | A | R | C |  | A | C |  |  | C
Requirements Gathering/ Analysis/ Discovery (Who, What, Why?)
– Conduct stakeholder meetings & workshops | Meeting Minutes & Notes |  | R | C |  | A | C |  |  | C
– Gather requirements | Requirements Document | I | R | C |  | A | C | C |  | C
– Approval process | Get sign-off on requirements | A | R | C |  | A | C | C |  | C
Design/ Specification(How?)
– Gather business requirements | Business Requirements Document (BRD) | I | R | C |  | A | C | C |  | C
– Identify system requirements | Software Requirements Specification (SRS) | I | R | C |  | A | C | C |  | C
– Identify non-functional requirements (security, performance, compliance) | Non-Functional Requirements (NFR) Document | I | R |  |  | A | C | C |  | C
– Create wireframes and mockups | UI/UX Design Mockups & Wireframes | I | C | A/C | R | I | C
– Create database schema & data models | Database Design Document (HLD, LLD) | I | C |  |  | A | C | R |  | C
– Define epics, user stories and acceptance criteria | Feature map and acceptance criteria document | I | R | C |  | A | C | C |  | C
– Conduct reviews and approvals | Sign-off Document | A | R | C |  | A | C |  |  | C
Development (Implementation)
– Develop new features | Feature Implementation Document | I | C | C |  | A | C | R | R
– Perform unit testing | Unit Test Cases & Unit Test Report |  |  |  |  | I | C | A | R
– Code reviews & approvals | Peer code reviews and merge approvals |  |  |  |  | I | C | A | R
Testing
– Develop test plan | Test Plan Document | I | C | C |  | A | C | C |  | R
– Write test cases | Test Cases Document |  | C | C |  | A |  |  | C | R
– Execute functional, regression, and performance testing | Test Execution Report |  | C |  |  | A |  |  | C | A/R
– Identify & log defects | Defect Log / Bug Report |  |  |  |  | I |  |  | C/I | A/R
– Conduct user acceptance testing (UAT) | User Acceptance Test Report | I | R | C |  | A |  | C | I | R
– Approval process | Sign-Off Document |  | R |  |  | A |  |  | I | R
Deployment
– Deploy website to production servers | Deployment Checklist by DevOps |  | I | I |  | A |  | C | I | C | R
– Conduct post-launch review | Lessons Learned Document |  | R | C |  | A |  | C | I | C | C
– Create Project Closure Report | Project Closure Report | I | R | C |  | A |  | C | I | C | C
Maintenance
– Implement new feature enhancements | Feature Enhancement Plan & Release Notes |  | R | C | R | A | C | R | R | R | R
Role
Project Deliverable
(or Activity)